## Sheet1
Team 6: |  |  | Face-recognition and Attendance system
Sokhom Panha Vathana
Chheng SreyMeas
| Action | Responsible | Start Date | End Date | Budget | Status | Progress | Note
Week #1: Researching
| Find Reference |  | 13/2/2023 | 18/2/2023 | None | Started | 100%
| Download library |  | 13/2/2023 | 18/2/2023 | None | Started | 100%
| Open ESP32 CAM |  | 13/2/2023 | 18/2/2023 | None | Started | 0%
| Discussing | Group | 17/2/2023 | 17/2/2023 | None | Started | 0% | We must meet up
Week #2: coding
Face detection
Face recognition with python
Face recognition with camera
| Discussing | Group | [5 empty] | We must meet up
Week #3: coding
Face-recognition with esp32 cam
set 3 person image
recognition all image
| Discussing | Group | [5 empty] | We must meet up
Week #4: coding
Show their name on screen
show time that camera detect
show name and time on screen
| Discussing | Group | [5 empty] | We must meet up
Week #5: connecting
connect esp32 to exel
connect esp32 to exel show name
connect esp32 to exel show time
| Discussing | Group | [5 empty] | We must meet up
Week #6: testing
detect and send data to exel
data has time/name/id
test send data to mobile phone
| Discussing | Group | [5 empty] | We must meet up
Week #7: hardwear
design 3D box on fusion 360
print box out
combine all component
| Discussing | Group | [5 empty] | We must meet up